|  |  |
| --- | --- |
| September - October | 2020 |
|  |  |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |
|  |  | 1 | 2 | 3 | 4 | 5 |
|  |  |  |  |  |  |  |
| 6 | 7 | 8 | 9 | 10 | 11 | 12 |
|  |  |  |  |  |  |  |
| 13 | 14 | 15 | 16 | 17 | 18 | 19 |
|  |  |  |  |  | Jam Start | Research music |
| 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| Research music | Meeting with team  Music Design | Music Design | Palette Setup | Main menu Theme & Revisions | Cues & Revisions | Cues & Revisions |
| 27 | 28 | 29 | 30 | 1 | 2 | 3 |
| Deadline for composition  Layback & Orchestration | Live Recording | Editing | Mixing | Mastering, Formatting & Delivery | Implementation | Implementation & Optimization |
| 4 | 5 |  |  |  |  |  |
|  | Game Jam Deadline |  |  |  |  |  |

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |